# Lucidic AI Pilot: POC Plan and Verizon Expectations

Trace-to-custom-model pilot through the Kairos LLM gateway

Varun Saagar, Verizon

12 October 2026 · Draft v0.1 for review

# Contents

- Executive summary and objectives

- Zero-process-change integration

- SaaS to Verizon network: deployment and governance

- POC scope and use cases

- POC test areas (TA-01 to TA-12)

- Mutual expectations

- Phased plan (about 8 weeks)

- Testimonial and beta-readiness criteria

- Pilot scorecard (weighted)

- Risks and mitigations

- Open questions for Lucidic

# Document control

| Item | Detail |
| --- | --- |
| Document | Lucidic AI pilot: POC plan and Verizon expectations |
| Version / status | v0.1, draft for internal review, then to be shared with Lucidic |
| Date | 12 October 2026 |
| Author | Varun Saagar, [title], Verizon |
| Executive sponsor | [owner] |
| Classification | [Verizon classification label]. Shared with Lucidic AI under the executed mutual NDA |
| Audience | Verizon pilot stakeholders (Kairos platform, Agent SDK, Security/TPRM, Privacy/Legal, Data/ML, use-case owners, Procurement) and the Lucidic AI team |
| Basis | Public Lucidic materials (lucidic.ai, YC profile, Launch HN, demo video) and a static review of the public lucidicai SDKs (Python 3.7.1, TypeScript 2.2.2). No Lucidic backend was called. Lucidic is asked to confirm or correct every SDK-derived finding (Section 11). |

How to read this document. Statements of the form “Lucidic must …” are Verizon’s POC requirements. Values in square brackets (for example [owner] and [metric target]) are placeholders to be agreed before Week 1. Nothing in this document describes Verizon internal systems beyond what is stated in Section 1.3.

# 1. Executive summary and objectives

## 1.1 Summary

Verizon proposes an 8-week proof of concept (POC) with Lucidic AI (YC W25). Lucidic trains custom models and agent harnesses (system prompts, context, tools, memory, guardrails and policies) from production traces. The POC will take one internal, low-CPNI agent use case end to end: from roughly three months of historical OpenTelemetry (OTel) traces, through simulation, harness optimisation, memory and fine-tuning, to a custom model served behind Verizon’s Kairos LLM gateway.

Three conditions are non-negotiable:

- Zero process change. Lucidic integrates through Kairos (LiteLLM) and Verizon’s existing OTel pipeline, with no changes to application code.

- Data stays governed. CPNI/PII is redacted inside the Verizon boundary before any data egress, and the deployment model passes Verizon third-party risk management (TPRM).

- Portable outcome. Trained weights and the harness are exportable and run behind Kairos without the Lucidic runtime on the inference path.

If the POC meets its gates and score threshold (Section 9), the result becomes an internal testimonial and a beta offering for other Verizon agent teams (Section 8).

## 1.2 Objectives

| # | Objective | Measured by |
| --- | --- | --- |
| O1 | Prove zero-code-change integration via Kairos and the existing OTel pipeline | TA-01, TA-02 |
| O2 | Prove that simulations built from Verizon traces are faithful enough to drive optimisation decisions | TA-03, TA-04 |
| O3 | Demonstrate measurable lift from harness optimisation and memory on a held-out set | TA-05, TA-06 |
| O4 | Produce a custom model that matches or beats the current production model on quality at lower cost and/or latency | TA-07, TA-09 |
| O5 | Prove portability: weights and harness exported, served behind Kairos, no Lucidic runtime dependency at inference | TA-08 |
| O6 | Clear security, privacy and vendor-risk requirements for a production path | TA-10, TA-11, TA-12 |
| O7 | Produce the artefacts needed to offer the pattern to other Verizon teams as a beta | Section 8 |

## 1.3 Verizon context (as relevant to this pilot)

- Internal agent SDK. Verizon agents are built on an internal agent SDK.

- Kairos. A Laravel-based gateway built on LiteLLM. Every model call goes through Kairos.

- Tracing. Existing OTel traces in Galileo format, about three months of history.

- Target pipeline: OTel traces → simulation → harness optimisation → memory → fine-tuning → custom model.

Figure 1. Target pilot architecture: Kairos and the OTel Collector as the only integration points; custom model served back behind Kairos.

# 2. Zero-process-change integration

## 2.1 Requirement

Lucidic must integrate through Kairos (LiteLLM) and Verizon’s existing OTel/Galileo pipeline without changes to agent application code. Configuration of Kairos, the OTel Collector, or a Verizon-owned adapter service is acceptable. Adding the lucidicai SDK, decorators, or session wrappers to agent code is not acceptable for this POC.

## 2.2 What the public SDK tells us (to be confirmed by Lucidic)

| Finding | Evidence (SDK 3.7.1) | Implication for Verizon |
| --- | --- | --- |
| No OTLP. Neither SDK contains an OTLP exporter or receiver; data goes to Lucidic’s proprietary JSON REST API (/api/initsession, /api/events, /api/sdk/datasets/...). | telemetry/lucidic_exporter.py, event_queue.py | Our existing OTel/Galileo traces cannot be sent as-is. We need an OTLP endpoint from Lucidic or a Verizon-side adapter. |
| Spans without lucidic.session_id are dropped. The exporter drops any span lacking a session id (attribute or context variable). | telemetry/lucidic_exporter.py l.113-124 | Gateway-level spans must be stamped with a session id derived from existing request metadata, or grouped into sessions by an adapter. |
| LiteLLM is already instrumented. The SDK ships a LiteLLM callback bridge. | telemetry/litellm_bridge.py | A Kairos-side LiteLLM callback is technically plausible, subject to session context and redaction. |
| Tool mocking requires @mockable decorators. Tool signatures and source_hash are synced from decorated functions; mock calls are served per session from DuckDB fixtures. | api/resources/agent_tools_sync.py, mock_call.py, session_init_fixtures.py | Decorating tools is a code change in Verizon agents. We ask for gateway- or trace-based tool mocking instead (Section 2.4). |
| No masking on the v3 exporter path. masking_function is applied only in the legacy span processor. | sdk/session.py, providers/lucidic_span_processor.py | Assume no vendor-side redaction. Redact at the Verizon OTel Collector before egress. |
| Endpoint override exists. LUCIDIC_BASE_URL and LUCIDIC_REGION (us, india). | core/config.py l.37-59 | Supports a dedicated or private endpoint and egress allow-listing (Section 3). |
| Trained modules are served by the Lucidic backend. sdk/training-modules/inferences. | api/resources/training_modules.py | Inference via Lucidic would bypass Kairos controls. Not acceptable for production (Section 2.3, option D). |

## 2.3 Integration options

Option A: LiteLLM callback/logger for Lucidic inside Kairos (live capture). Register a Lucidic callback in Kairos’s LiteLLM layer (the SDK’s LiteLLM bridge, or a Lucidic-supplied LiteLLM CustomLogger). Kairos already sees every model call, including tool-call requests and tool results carried in message history.

- Pros: single choke point; no agent change; captures model, route, tokens, latency and cost.

- Cons: needs a session id per conversation, derived from existing request metadata or headers (whether the internal SDK already propagates one to Kairos is to be confirmed by the Kairos owner); gateway sees model calls but not tool execution internals; redaction must run before the callback ships data; adds a vendor dependency in the gateway hot path, so it must be asynchronous and fail-open.

- Constraint: Kairos is Laravel-based on top of LiteLLM. Where the callback runs depends on whether the LiteLLM component is the Python proxy. [Kairos owner to confirm.]

Option B: OTLP ingestion endpoint provided by Lucidic (requested). Lucidic exposes a standard OTLP/HTTP or OTLP/gRPC endpoint that accepts GenAI semantic-convention and OpenInference spans and maps them to sessions and events server-side, with a configurable session key (for example session.id, gen_ai.conversation.id or trace id).

- Pros: standards-based; reuses the existing Collector; same path for live and historical data; no Verizon-maintained mapping code.

- Cons: does not exist in the public SDK today; depends on Lucidic delivery and its mapping of Galileo-specific attributes.

Option C: OTel Collector plus a Galileo-OTel → Lucidic adapter (Verizon-owned, interim). The Verizon OTel Collector receives spans from Kairos and the agent SDK, then redacts, normalises and fans out. A small adapter service (and a batch reader for the three-month archive) groups spans into sessions and calls Lucidic’s session, event and dataset APIs.

- Mapping: trace/session → initsession (tags: use case, Kairos route, outcome); LLM span → llm_generation event (messages, output, model, tokens, cost, duration, parent); tool span → tool event; outcome label → eval or session success flag; representative sessions → dataset items (seed simulation fixtures).

- Engineering: idempotency (client_event_id = span id), rate limiting, dead-letter queue, reconciliation counts.

- Pros: works today; a single control point for redaction; covers historical and live data.

- Cons: Verizon maintains the mapping against a proprietary, undocumented schema; breaks if the schema changes.

Option D: custom model served behind Kairos as a LiteLLM model route (return path). Exported weights are served on Verizon infrastructure (for example vLLM or an equivalent OpenAI-compatible server) and registered in Kairos as a normal LiteLLM route (for example lucidic-[use-case]-v[n]). Shadow, canary and rollback are controlled by Kairos routing. The optimised harness (prompts, tool descriptions, policies) is delivered as plain configuration loaded through existing prompt/config mechanisms, not through the Lucidic SDK. Memory/“Training Module” tools, if used, run inside the Verizon boundary and are exposed as standard tools (for example via MCP or an OpenAI-compatible tool endpoint).

- Pros: keeps routing, quotas, logging and guardrails in Kairos; no Lucidic runtime at inference; reversible.

- Cons: requires Lucidic to export weights and harness in open formats, and Verizon to provide serving capacity.

Recommended integration pattern. Option C for historical ingest and Weeks 1–2, moving to Option B once Lucidic delivers OTLP; Option A only if Lucidic supplies a fail-open, async LiteLLM logger and the Collector cannot provide the needed fidelity; Option D is mandatory for any custom model or harness that reaches users.

## 2.4 Tool mocking without code change

Simulation requires tool behaviour. Decorating tools with @mockable is a code change, so Verizon asks Lucidic to support one or both of:

- Trace-based tool mocking. Build per-session fixtures directly from tool calls and tool results observed in traces (tool spans from the agent SDK and tool messages visible at Kairos), with tool schemas supplied by Verizon as JSON Schema/OpenAPI files rather than synced from code.

- Gateway-level simulation. Run the agent’s harness (prompts, tool schemas, policies) inside Lucidic’s simulator, with the simulator answering tool calls, so the Verizon agent code does not need to run or be modified.

Lucidic should state how drift detection (today based on source_hash) works without code access, and how fixture fidelity is validated.

## 2.5 Routing confound

Kairos routing can change which model answered a given turn, which confounds harness evaluation. Every span must carry the routing decision (kairos.route, policy, resolved model). During simulation the route is pinned; routing policy is treated as a fixed variable unless Lucidic can model it explicitly as a harness parameter.

## 2.6 What Lucidic must deliver (integration)

- A written, versioned schema for sessions, events and tool events, and a supported bulk-import path for historical traces.

- An OTLP ingest endpoint (GenAI semconv and OpenInference) with a configurable session key, or a committed date for one. [date]

- Confirmation of span-drop behaviour and a server-side option to group sessionless spans by a configurable key.

- Trace-based or gateway-level tool mocking with no @mockable requirement.

- If Option A is used: a LiteLLM logger that is asynchronous, fail-open, bounded-queue, and honours Verizon redaction.

- Export of trained weights (for example safetensors, with tokenizer and config) and harness (plain text/JSON/YAML), runnable without the Lucidic runtime.

- In-boundary deployment of any memory or Training Module components used at inference.

- Cost and latency computed from Kairos-supplied values, not the SDK’s local price table.

Figure 2. Lucidic offering map, derived from the public SDK: SDK surfaces (left) and backend capabilities (right).

# 3. SaaS to Verizon network: deployment and governance

## 3.1 Deployment options

A. Single-tenant deployment in a Verizon cloud account (VPC). Lucidic’s platform is deployed into a Verizon-owned account, either BYOC (Verizon operates, Lucidic supports) or managed (Lucidic operates through scoped, audited access). Data, training compute and weights stay in Verizon’s account.

B. Private connectivity (AWS PrivateLink or equivalent private service connect). A dedicated Lucidic tenant in Lucidic’s cloud, reached over private endpoints rather than the public internet. Data still leaves Verizon’s account but not over public networks.

C. Self-hosted / on-prem in Kubernetes. Lucidic ships container images and Helm charts; Verizon runs everything, including GPU training. The SDK currently shows no installer, so this depends on vendor packaging.

D. Hybrid control plane / data plane split. Lucidic hosts the control plane (UI, orchestration, experiment metadata); the data plane (trace store, simulators, training jobs, weights) runs in Verizon’s account. Only metadata and approved aggregates cross the boundary.

E. SaaS with egress allow-listing. Point the adapter at a dedicated tenant via LUCIDIC_BASE_URL, allow-list only that host on egress, and send only Collector-redacted data. The SDK also supports an India region (in.backend.lucidic.ai). Use of any region requires a Privacy/Legal residency determination; the default for US-origin data is a US-hosted path.

## 3.2 Decision table

Readiness values are unknown until Lucidic confirms (Section 11, questions 12 to 17).

| Criterion | A. VPC (BYOC / managed) | B. PrivateLink | C. Self-hosted K8s | D. Hybrid CP/DP | E. SaaS + allow-list |
| --- | --- | --- | --- | --- | --- |
| Raw trace data leaves Verizon account | No | Yes (private path) | No | No (metadata only) | Yes (redacted only) |
| Weights stay in Verizon | Yes | Contractual | Yes | Yes | Contractual |
| Vendor readiness | [confirm] | [confirm] | Unlikely near-term | [confirm] | Available (US/India) |
| Time to stand up | Weeks | Weeks | Longest | Weeks | Days |
| Verizon operating burden | Medium (BYOC high) | Low | High (incl. GPUs) | Medium | Low |
| TPRM / CPNI posture | Strongest | Medium | Strongest | Strong | Weakest; internal, redacted data only |
| Lock-in / exit | Low | Medium | Lowest | Low | Highest |
| Fit for POC | Good if ready | Good | Poor (time) | Good if ready | Acceptable with conditions |
| Fit for production | Preferred | Acceptable for low-sensitivity data | Acceptable | Preferred | Not acceptable for CPNI |

## 3.3 Recommendation

- POC: a dedicated Lucidic tenant on a US-hosted path, reached via PrivateLink (B) if available, otherwise SaaS with strict egress allow-listing (E). Conditions: an internal, low-CPNI use case only; redaction at the Verizon Collector before egress; no Lucidic calls on the inference path; all training artefacts exported to Verizon at the end of the POC; deletion certified at exit.

- Production: single-tenant in Verizon’s cloud account (A, managed preferred) or hybrid with the data plane in Verizon (D). Customer-facing or CPNI-bearing use cases are only in scope on A, C or D.

- Decision owner: [Security architecture owner] with [Privacy/Legal owner]; decision required by end of Week 0.

## 3.4 Governance path

| Control | Verizon expectation | Evidence from Lucidic | Gate |
| --- | --- | --- | --- |
| TPRM / vendor security review | Complete Verizon TPRM questionnaire and risk tiering | Completed questionnaire, architecture, data-flow diagram, subprocessor list | Before any Verizon data egress |
| SOC 2 Type II | Current report, or report status and bridge letter | SOC 2 Type II report (or Type I plus remediation plan and timeline) | Before data egress (POC tier per TPRM) |
| Penetration test | Independent test within the last 12 months | Executive summary and remediation status | Before data egress |
| DPA | Signed data processing agreement covering purpose limitation, subprocessors, breach notice, deletion | Signed DPA | Before data egress |
| CPNI/PII redaction | Redaction and tokenisation at the Verizon Collector before egress; vendor treats data as confidential regardless | Confirmation no un-redacted data required; vendor-side masking roadmap | Redaction test pass (TA-10) |
| Data residency | Region set by Privacy/Legal determination; US path default for US-origin data | Hosting regions, backups, support access locations, subprocessors | Week 0 |
| Encryption and KMS | TLS 1.2+ in transit; AES-256 at rest; customer-managed keys (BYOK) for production | Key management design; BYOK support | POC: vendor keys acceptable [confirm]; production: BYOK |
| SSO/SAML and RBAC | SAML/OIDC SSO with Verizon IdP; role-based access; SCIM preferred | Admin guide, role model | Before user onboarding |
| Audit logs | Exportable logs of user, admin, API and support access | Sample log export; SIEM integration options | Week 1 |
| Retention and deletion | Pilot data retained only for the POC term; deletion on request and at exit with certificate | Retention configuration; deletion certificate | Exit |
| Model weight ownership and export | Verizon owns trained weights, harness and derived artefacts; open-format export | Contract clause; export demonstrated (TA-08) | Before Phase 4 |
| Source-code escrow and exit plan | Escrow for production; documented exit plan and transition support | Escrow terms; exit runbook | Before production contract |

# 4. POC scope and use cases

## 4.1 Candidate use cases (to be confirmed)

The POC targets one use case end to end, with an optional second for generalisation. Both candidates are internal and are listed for confirmation by the business owners.

| Attribute | Candidate 1: IT helpdesk / employee productivity | Candidate 2: Frontline rep assist |
| --- | --- | --- |
| Status | Candidate, to confirm with [use-case owner] | Candidate, to confirm with [use-case owner] |
| Why it fits | Clear resolution labels; ITSM and knowledge tools are mockable; low CPNI exposure | Retrieval and knowledge tools are mockable; measurable answer acceptance and handling time |
| Reward signals | [ticket resolved / deflected], [reopen rate], [CSAT if captured] | [answer accepted], [handling-time proxy], [escalation rate] |
| Data sensitivity | Employee PII; low CPNI | Medium: conversation snippets may contain CPNI |
| Trace availability | [N sessions in 3-month window] | [N sessions in 3-month window] |
| Recommendation | Primary | Secondary, only after redaction is proven on Candidate 1 |

## 4.2 Why customer-facing work waits

Customer-facing assistants carry CPNI and customer PII in prompts, completions and tool payloads, and act on billing, account and order systems. The public SDK ships full prompts, completions and images and applies no masking on its current path. Customer-facing use cases are therefore out of scope until (a) CPNI handling is approved by Privacy/Legal, (b) the production deployment model (Section 3.3) is in place, (c) redaction is proven at scale, and (d) the DPA and residency terms are settled.

## 4.3 In scope / out of scope

- In scope: historical trace ingest; live capture through the Collector/Kairos for the chosen use case; simulation, replay and branching; harness optimisation; memory; fine-tuning of one custom model; export; shadow/offline serving behind Kairos; security review for the POC tier.

- Out of scope: customer-facing traffic; production rollout to end users; changes to agent application code; changes to Kairos routing policy beyond adding a new route; Lucidic runtime on the inference path.

# 5. POC test areas

Each test area has an owner, explicit success criteria, and required evidence. Baselines are measured in Phase 2 on the same held-out set and evaluation harness used for every later comparison. “Held-out” means sessions never used for simulation building, optimisation or training.

### TA-01. Integration via Kairos

| Aspect | Detail |
| --- | --- |
| What we test | Live capture through Kairos and the Collector (Options A/B/C) with no agent code change; session grouping; routing metadata; gateway overhead and fail-open behaviour |
| Success criteria | 0 app code changes; ≥ [99]% of in-scope model calls captured as Lucidic events with correct session grouping; added p95 gateway latency ≤ [X ms]; Lucidic outage causes 0 failed user requests |
| Evidence | Change log (config only); reconciliation report (Kairos call count vs Lucidic events); latency benchmark; fault-injection test result |
| Owner | [Kairos owner] / [Lucidic engineer] |

### TA-02. Historical trace ingest

| Aspect | Detail |
| --- | --- |
| What we test | Bulk import of about three months of Galileo-format OTel traces via adapter or bulk/OTLP endpoint |
| Success criteria | ≥ [99]% of spans mapped; 0 silently dropped spans (every drop logged with reason); parent/child and tool linkage preserved; 0 un-redacted CPNI/PII in the vendor tenant; import of the full slice in ≤ [X hours] |
| Evidence | Mapping specification; reconciliation counts by span type; drop log; redaction scan report on vendor-side data sample |
| Owner | [Data engineering owner] |

### TA-03. Simulation fidelity

| Aspect | Detail |
| --- | --- |
| What we test | Environments built from traces with trace-based tool mocking; agreement between simulated and production outcomes |
| Success criteria | Replayed baseline task success within ±[5] pp of production on the held-out set; tool-mock coverage ≥ [90]% of tool calls; SME blind review rates ≥ [80]% of sampled simulated sessions as realistic |
| Evidence | Sim-vs-real comparison report; mock coverage report; SME review sheet; list of unmockable tools and handling |
| Owner | [ML/eval lead] / [Lucidic] |

### TA-04. Replay and branching

| Aspect | Detail |
| --- | --- |
| What we test | Replay any production session; branch from any step with a changed harness or model; determinism and repeatability |
| Success criteria | Branch from step N works for ≥ [95]% of sampled sessions; repeated runs give stable metrics (variance ≤ [X]); route pinned and recorded |
| Evidence | Demonstration on [N] sessions chosen by Verizon; run logs; variance analysis |
| Owner | [ML/eval lead] |

### TA-05. Harness optimisation lift

| Aspect | Detail |
| --- | --- |
| What we test | Optimisation (for example EvoSim) over prompts, tool descriptions, context, policies and guardrails, holding the model fixed |
| Success criteria | ≥ +[X] pp task success on held-out set vs baseline, with no regression > [Y] pp on safety/policy evals; statistically significant at [95]% confidence; harness exported as readable config |
| Evidence | Before/after eval report with confidence intervals; diff of the harness; list of tuned parameters and search budget |
| Owner | [ML/eval lead] / [Lucidic] |

### TA-06. Memory

| Aspect | Detail |
| --- | --- |
| What we test | How memory is learned from traces, stored, retrieved and served; incremental lift over the optimised harness |
| Success criteria | Additional ≥ +[X] pp over TA-05; memory contents inspectable and deletable; no PII persisted in memory; runs inside the Verizon boundary at inference (production requirement) |
| Evidence | Ablation (harness only vs harness + memory); memory content export; PII scan; deployment diagram |
| Owner | [ML/eval lead] |

### TA-07. Fine-tuning to a custom model

| Aspect | Detail |
| --- | --- |
| What we test | SFT/RL of a custom model from Verizon traces, co-trained with the harness; base-model choice and licence |
| Success criteria | Quality ≥ current production model on held-out set (within [X] pp or better); cost per task ≤ [Y]% of baseline; base-model licence approved by Legal; training location approved |
| Evidence | Training report (base model, data, method, compute location); eval report; model card; licence review |
| Owner | [ML/eval lead] / [Legal] |

### TA-08. Weight and harness export; serving behind Kairos

| Aspect | Detail |
| --- | --- |
| What we test | Export of weights and harness in open formats; serving on Verizon infrastructure as a Kairos LiteLLM route; no Lucidic runtime calls |
| Success criteria | Weights load in a standard runtime (for example vLLM); exported model reproduces the vendor-reported eval within ±[2] pp; 0 calls to Lucidic hosts during inference (egress logs); route supports shadow and rollback |
| Evidence | Export package manifest and checksums; serving config; reproduced eval; egress log extract; shadow-traffic report |
| Owner | [Kairos owner] / [ML platform owner] |

### TA-09. Latency and cost

| Aspect | Detail |
| --- | --- |
| What we test | End-to-end latency and unit cost of the custom model and optimised harness vs baseline, measured by Kairos |
| Success criteria | p50/p95 latency ≤ [targets]; cost per resolved task ≤ [Y]% of baseline; total cost of ownership (serving + licence + training refresh) within [budget] |
| Evidence | Kairos latency and cost reports; TCO model |
| Owner | [Kairos owner] / [Finance partner] |

### TA-10. Security and compliance

| Aspect | Detail |
| --- | --- |
| What we test | Governance controls in Section 3.4 for the POC tier; redaction effectiveness; access control; auditability |
| Success criteria | TPRM approved for POC tier; redaction recall ≥ [99.x]% on a labelled test set; SSO and RBAC in place; audit logs exported; deletion certificate at exit |
| Evidence | TPRM decision; redaction test report; access review; audit log sample; deletion certificate |
| Owner | [Security owner] / [Privacy owner] |

### TA-11. Operability and support

| Aspect | Detail |
| --- | --- |
| What we test | Day-to-day operation: onboarding effort, documentation, monitoring, incident handling, support responsiveness |
| Success criteria | Support response ≤ [X business hours] for P1/P2; documented runbooks for ingest, training and export; Verizon team can run an optimisation cycle with ≤ [X] vendor touchpoints; effort within [person-days] |
| Evidence | Support ticket log; runbook drafts; effort tracker; team survey |
| Owner | [Pilot lead] |

### TA-12. Vendor maturity

| Aspect | Detail |
| --- | --- |
| What we test | Viability and continuity: team, funding, roadmap, references, security programme, contract terms |
| Success criteria | Credible roadmap for OTLP, VPC and export items; references available [Y/N]; escrow and exit plan acceptable; financial and continuity review passed by Procurement |
| Evidence | Roadmap letter; references; escrow terms; Procurement review |
| Owner | [Procurement owner] |

# 6. Mutual expectations

## 6.1 What Lucidic can expect from Verizon

| Area | Verizon provides | Timing |
| --- | --- | --- |
| Data access | Redacted export of the three-month trace slice for the chosen use case (~[N] sessions), via adapter or file drop | Week 1–2, after Week 0 gates |
| Trace samples | [N] representative sessions, plus a data dictionary for Galileo span attributes and Kairos metadata | Week 0 (synthetic or fully redacted) |
| Tool schemas | JSON Schema/OpenAPI for in-scope tools, with example inputs and outputs | Week 1 |
| Reward / eval definitions | Outcome labels, success definition, rubric, safety/policy checks, held-out set definition | Draft Week 1, frozen end of Week 2 |
| SMEs | [N] hours/week from use-case SMEs for rubric design and simulation review | Weeks 1–8 |
| Environments | Sandbox endpoint for Collector/adapter; serving environment for the custom model behind Kairos | Week 1 (adapter); Week 5 (serving) |
| Credentials | Scoped service accounts and API keys under Verizon secrets management; SSO for named users | Week 0–1 |
| Timelines and governance | Named owners (RACI), weekly status, decisions within agreed SLAs | Throughout |

## 6.2 What Verizon expects from Lucidic

| Area | Lucidic provides |
| --- | --- |
| Team | Named engagement lead and engineer(s); weekly working session; escalation contact |
| Integration | Items in Section 2.6, with confirmation or correction of all SDK findings in Section 2.2 |
| Platform | Dedicated tenant on an agreed region and connectivity model; SSO; RBAC; audit logs |
| Method transparency | Documentation of simulation, optimisation (EvoSim/GA/RL/Bayesian) and training methods sufficient for Verizon to reproduce evaluations |
| Evaluation | Reports against the frozen held-out set; raw per-session results, not only aggregates |
| Artefacts | Exported weights, harness, memory contents, eval sets, configs and model card, delivered to Verizon |
| Security | Section 3.4 evidence pack; incident notification within [X hours] |
| Commercials | POC pricing, conversion terms, production pricing model and support SLA |
| Exit | Data deletion with certificate; transition support |

# 7. Phased plan (about 8 weeks)

| Phase | Weeks | Activities | Exit gate / deliverables |
| --- | --- | --- | --- |
| 0. Security and access | W0 | TPRM intake; DPA; residency decision; deployment option chosen; SSO and accounts; redaction rules agreed; synthetic sample shared | Data-egress approval; signed DPA; tenant provisioned |
| 1. Integration | W1–W2 | Collector redaction pipeline; adapter (Option C) or OTLP (Option B); historical import; live capture test; tool schemas shared | TA-01, TA-02, TA-10 (redaction) passed |
| 2. Baseline and simulation | W2–W3 | Reward/eval definitions frozen; held-out set fixed; environments built; sim-vs-real validation; replay/branch tests | Baseline report; TA-03, TA-04 |
| 3. Harness and memory | W4–W5 | Harness optimisation runs; memory build and ablation; harness export | TA-05, TA-06 |
| 4. Custom model | W6–W7 | Base model chosen and approved; fine-tune/RL; export; serving behind Kairos; shadow traffic; latency/cost | TA-07, TA-08, TA-09 |
| 5. Readout | W8 | Scorecard; operability and vendor review; testimonial draft; go/no-go and commercial proposal | TA-11, TA-12; scorecard; decision memo |

## 7.1 RACI

R = Responsible, A = Accountable, C = Consulted, I = Informed. Named owners per role: [owner] (to be assigned in Week 0). Pilot lead: Varun Saagar [confirm]. “SMEs” = use-case owner and SMEs.

| Activity | Sponsor | Pilot lead | Kairos | Agent SDK | Data eng | ML/eval | Security | Privacy/ Legal | SMEs | Procurement | Lucidic |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TPRM, DPA, residency | I | R | C | I | I | I | A | R | I | R | C |
| Deployment option decision | A | R | C | I | C | C | R | C | I | I | C |
| Collector redaction | I | C | C | C | R | I | A | C | I | I | I |
| Adapter / OTLP ingest | I | A | C | C | R | C | C | I | I | I | R |
| Reward and eval definitions | I | A | I | C | I | R | I | I | R | I | C |
| Simulation and replay | I | A | I | C | C | R | I | I | C | I | R |
| Harness and memory optimisation | I | A | I | C | I | R | I | I | C | I | R |
| Fine-tuning and export | I | A | C | I | I | R | C | C | I | I | R |
| Serving behind Kairos | I | A | R | C | I | C | C | I | I | I | C |
| Scorecard and readout | A | R | C | C | C | R | C | C | C | C | C |
| Commercials | A | C | I | I | I | I | I | C | I | R | R |

# 8. Testimonial and beta-readiness criteria

The POC result is offered to other Verizon teams as a beta only when the internal evidence below exists. “Testimonial” means an internal, evidence-backed case study, not marketing material; any external reference by Lucidic requires separate Verizon approval.

## 8.1 Entry criteria for beta

| Criterion | Threshold |
| --- | --- |
| Scorecard | Weighted score ≥ [75]/100 and all gates passed (Section 9) |
| Quality lift | Held-out lift ≥ +[X] pp task success (harness and/or model), sustained in ≥ [2] weeks of shadow traffic |
| Cost / latency | Cost per resolved task ≤ [Y]% of baseline; p95 latency ≤ [Z ms] |
| Zero process change | Second use case onboarded via config only (or a credible plan, if only one use case ran) |
| Portability | Custom model and harness served behind Kairos with no Lucidic inference dependency |
| Security | Production deployment model agreed; TPRM production tier approved or on a defined path |
| Effort | Onboarding a new team ≤ [N] person-days Verizon effort |

## 8.2 Required artefacts

- Case study (template below).

- Metrics pack: baseline vs optimised results with confidence intervals, per-session data, cost and latency from Kairos.

- Runbook: ingest, redaction, simulation, optimisation, training, export, serving, rollback, incident handling, deletion.

- Onboarding guide for new teams: prerequisites, data requirements, reward design guidance, tool schema format, Kairos route registration, expected timeline and effort.

- Reference architecture and data-flow diagram approved by Security.

- Security and compliance pack: TPRM decision, DPA, redaction test, residency decision.

- Commercial model: unit pricing and TCO per use case.

## 8.3 Case study template

| Section | Content |
| --- | --- |
| Use case and team | [use case], [team], [users affected] |
| Problem and baseline | Baseline metrics on the held-out set, period, model and route |
| Approach | Data used (volume, period, redaction), simulation, harness changes, memory, model |
| Results | [task success Δ], [resolution/CSAT Δ], [cost Δ], [latency Δ], with confidence intervals |
| What changed in production | Kairos route, harness config version, rollout scope |
| Effort and timeline | Verizon person-days, vendor touchpoints, elapsed weeks |
| Risks and limitations | Fidelity gaps, unmockable tools, known regressions |
| Recommendation | Who should adopt, prerequisites, next use cases |
| Approvals | Use-case owner, Security, Privacy/Legal, Exec sponsor |

# 9. Pilot scorecard (weighted)

Each scored area is rated 0–5 against its TA criteria and multiplied by its weight / 5. Gate items are pass/fail: any gate failure means no-go regardless of total score. Proposed decision thresholds: ≥ [75] go to production planning; [60–74] extend or re-scope; < [60] stop.

| # | Criterion | Linked TA | Gate | Weight |
| --- | --- | --- | --- | --- |
| 1 | Zero-code-change integration via Kairos/Collector | TA-01 | Gate | 10 |
| 2 | Historical ingest: ≥ [99]% mapped, 0 un-redacted CPNI/PII | TA-02 | Gate | 10 |
| 3 | Simulation fidelity within ±[5] pp; replay/branching | TA-03, TA-04 |  | 15 |
| 4 | Harness optimisation and memory lift on held-out set | TA-05, TA-06 |  | 20 |
| 5 | Custom model quality vs production baseline | TA-07 |  | 15 |
| 6 | Portability: weights and harness served behind Kairos, no Lucidic runtime | TA-08 | Gate | 10 |
| 7 | Latency and cost vs baseline | TA-09 |  | 10 |
| 8 | Security and compliance (POC tier) | TA-10 | Gate | 5 |
| 9 | Operability and support | TA-11 |  | 3 |
| 10 | Vendor maturity and commercial terms | TA-12 |  | 2 |
|  | Total |  |  | 100 |

# 10. Risks and mitigations

| # | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | No OTLP ingest; proprietary schema changes break the adapter | High | Medium | Option C adapter with versioned mapping and contract tests; request OTLP (Option B) with a date | [Data eng] |
| R2 | Spans dropped for missing session id, silently biasing data | High | High | Stamp session ids at Collector/adapter; reconciliation counts; drop log required | [Data eng] |
| R3 | Tool mocking requires @mockable code changes | High | High | Require trace-based or gateway-level mocking; out-of-scope tools documented | [Lucidic] |
| R4 | CPNI/PII egress (no masking on vendor v3 path) | Medium | High | Collector redaction before egress; internal use case only; redaction test as gate | [Security / Privacy] |
| R5 | Simulation not faithful; optimisation overfits the simulator | Medium | High | Sim-vs-real gate; held-out production sessions; shadow traffic before any claim | [ML/eval] |
| R6 | Kairos routing confounds evaluation | Medium | Medium | Record route on every span; pin route in simulation | [Kairos owner] |
| R7 | Inference bypasses Kairos via Lucidic runtime or Training Modules | Medium | High | Option D mandatory; egress deny-list for Lucidic hosts on inference path | [Kairos owner] |
| R8 | Weights or harness not exportable / IP unclear | Medium | High | Contract clause before Phase 4; export test as gate | [Legal / Procurement] |
| R9 | Vendor maturity: small team, early funding, product pivot | Medium | High | Escrow and exit plan; artefacts delivered to Verizon each phase; portable formats | [Procurement] |
| R10 | Gateway hot-path impact if a callback is used | Low | High | Async, fail-open, bounded queue; fault-injection test; prefer Collector path | [Kairos owner] |
| R11 | Residency mis-configuration (US vs India region) | Low | High | Privacy/Legal determination in Week 0; egress allow-list pinned to approved host | [Privacy] |
| R12 | Base-model licence unsuitable for Verizon use | Medium | Medium | Legal review of candidate base models in Week 3 | [Legal] |
| R13 | Insufficient labelled outcomes for rewards | Medium | Medium | SME rubric; LLM-judge calibrated against SME labels | [Use-case owner] |
| R14 | SME and team capacity | Medium | Medium | Hours committed in RACI; weekly checkpoint | [Pilot lead] |
| R15 | Benchmark claims not reproducible on Verizon data | Medium | Medium | Verizon-controlled held-out set and eval reproduced on exported model | [ML/eval] |

# 11. Open questions for Lucidic

Integration (Q-I)

- Is there, or will there be, an OTLP or bulk-import endpoint for foreign traces? Which semantic conventions (GenAI, OpenInference) are supported, and by when? [date]

- What is the authoritative schema for sessions, events and tool events? Is it versioned?

- Please confirm that spans without lucidic.session_id are dropped. Can sessions be grouped server-side by a configurable key?

- Can the LiteLLM bridge run as a standalone logger in a LiteLLM proxy deployment, asynchronously and fail-open?

- Can tool mocking be trace-based or gateway-level, with no @mockable decorators? How is drift detected without code access?

- Does masking apply on the v3 telemetry exporter path? Is vendor-side redaction on the roadmap?

- Can cost and latency be taken from Kairos values rather than the SDK price table?

Method (Q-M)

- How is simulation fidelity validated (sim-vs-real agreement), and what are typical results?

- Which harness parameters can EvoSim search? Can routing policy be fixed or treated as a parameter?

- What exactly are Training Modules (memory, knowledge, verify)? How is memory learned, stored, inspected and deleted?

- Which base models are supported for fine-tuning/RL, and what are their licences? Where does training run?

Deployment and security (Q-D)

- Q-D1: Is single-tenant deployment in a customer cloud account (BYOC or managed) available? Which clouds?

- Q-D2: Is PrivateLink or equivalent private connectivity available?

- Q-D3: Is self-hosted Kubernetes (images, Helm) available or planned?

- Q-D4: Is a control plane / data plane split available? What crosses the boundary?

- Q-D5: Where are the US and India regions hosted, including backups and support access? Who are the subprocessors?

- Q-D6: Status of SOC 2 Type II, latest pen test, BYOK/KMS, SSO/SAML, SCIM, RBAC and audit log export.

- What are default retention periods, and how is deletion certified?

Portability and commercial (Q-C)

- Can weights (for example safetensors plus tokenizer/config) and harness (plain config) be exported and run without the Lucidic runtime? Who owns them contractually?

- Will Lucidic agree to source-code escrow and a documented exit plan for production?

- POC pricing, conversion terms and production pricing model.

- Support model and SLA; team size dedicated to the engagement.

- Can Lucidic share enterprise references?

- Is lucidic.co (private rollout, on-prem tier) the same company or offering?

Placeholders in square brackets are to be agreed by named owners before Week 1. SDK-derived findings reflect a static review of public packages and are subject to confirmation by Lucidic.